## Jira Backlog
Issue Key | Issue Type | Summary | Epic | Assignee | Priority | Points | Sprint | Start Date | End Date
AWMS-01 | User Story | Secure User Login | EPIC-01 Auth & RBAC | Assigned to User | Highest | 3 | Sprint 1 (4 Wks) | 2026-10-08 | 2026-10-18
AWMS-02 | User Story | Role Assignment & RBAC | EPIC-01 Auth & RBAC | Assigned to User | Highest | 5 | Sprint 1 (4 Wks) | 2026-10-12 | 2026-10-22
AWMS-03 | User Story | View Inventory Balance | EPIC-02 Inventory | Assigned to User | High | 3 | Sprint 1 (4 Wks) | 2026-10-15 | 2026-10-25
AWMS-04 | User Story | Secure Inventory Update | EPIC-02 Inventory | Assigned to User | Highest | 5 | Sprint 1 (4 Wks) | 2026-10-18 | 2026-10-28
AWMS-05 | User Story | Register Autonomous Robot | EPIC-03 Robot Mgt | Assigned to User | Highest | 5 | Sprint 1 (4 Wks) | 2026-10-20 | 2026-11-01
AWMS-06 | User Story | Robot Command Authorization | EPIC-06 Robot Control | Assigned to User | Highest | 8 | Sprint 2 (4 Wks) | 2026-11-06 | 2026-11-20
AWMS-07 | User Story | Monitor Robot Status | EPIC-03 Robot Mgt | Assigned to User | High | 3 | Sprint 1 (4 Wks) | 2026-10-25 | 2026-11-05
AWMS-08 | User Story | Create Warehouse Task | EPIC-04 Task Mgt | Assigned to User | High | 5 | Sprint 1 (4 Wks) | 2026-10-25 | 2026-11-05
AWMS-09 | User Story | Assign AGV to Task | EPIC-04 Task Mgt | Assigned to User | Highest | 5 | Sprint 1 (4 Wks) | 2026-10-28 | 2026-11-05
AWMS-10 | User Story | Prevent Command Conflict | EPIC-06 Robot Control | Assigned to User | Highest | 8 | Sprint 2 (4 Wks) | 2026-11-12 | 2026-11-25
AWMS-11 | User Story | Prevent Replay Attack | EPIC-06 Robot Control | Assigned to User | Highest | 5 | Sprint 2 (4 Wks) | 2026-11-15 | 2026-11-28
AWMS-12 | User Story | Customer Order Placement | EPIC-05 Order Fulfillment | Assigned to User | High | 5 | Sprint 1 (4 Wks) | 2026-10-20 | 2026-11-05
AWMS-13 | User Story | Update Order Status via Tasks | EPIC-05 Order Fulfillment | Assigned to User | High | 5 | Sprint 2 (4 Wks) | 2026-11-06 | 2026-11-20
AWMS-14 | User Story | Security Audit Stream | EPIC-07 Audit & Mon | Assigned to User | High | 5 | Sprint 2 (4 Wks) | 2026-11-20 | 2026-12-01
AWMS-15 | User Story | Automated Security CI/CD | EPIC-08 Secure DevOps | Assigned to User | High | 5 | Sprint 2 (4 Wks) | 2026-11-25 | 2026-12-04