## Agile Approach
Parameter | Description | Security Integration Reason
Framework | Scrum with XP Security Practices | Combines iterative delivery (Scrum) with test-driven secure development, pair programming, and refactoring (XP).
Sprint Duration | 2 Weeks | Allows rapid security vulnerability triage and incremental security testing.

## Manifesto Mapping
Agile Manifesto Principle | AWMS Mapping & Security Practice
Customer Satisfaction | Continuous security checks and rapid delivery of order fulfillment features to customers.
Welcome Change | Modular RBAC and HMAC security architecture allowing new robot protocols without breaking core.
Deliver Working Software | Automated CI/CD security pipelines scanning dependencies and code on every push.
Daily Collaboration | Security Auditors work directly with Backend Developers to review audit logs and threat models.
Technical Excellence | Refactoring insecure modules to use JWT, bcrypt, HMAC-SHA256, and atomic database transactions.

## Refactoring Opportunities
Refactoring ID | Component | Before Code/Structure | After Code/Structure | Security Benefit
REF-01 | Robot Command Dispatcher | Insecure direct command execution without signature check | HMAC-SHA256 signature verification + Nonce anti-replay validation | Prevents unauthorized robot movement and replay attacks.
REF-02 | Inventory Management | Non-atomic direct quantity modification (stock = stock - qty) | SQLAlchemy with_for_update() transaction locking + reservation check | Prevents race conditions, negative inventory, and stock corruption.

## Agile Risks
Risk ID | Agile Limitation / Security Risk | Impact Level | Mitigation Strategy
RSK-01 | Over-focus on user features neglects architectural security controls | HIGH | Introduce explicit Security User Stories with story points in Sprints (EPIC-06, EPIC-07).
RSK-02 | Sprint velocity pressure leading to skipped security testing | HIGH | Mandatory CI/CD automated Bandit static analysis and pip-audit quality gates before pull request merge.